## Project Plan
Sovy - Digital Calculator PO1_DGC
First Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Team 1 | Nour & Nihal | HSI Document |  | 2021-02-11 | 2021-02-14 | 2021-02-11 | 2021-02-14 | 5 | 3
Team 2 | Habiba & Abdullah | CRS |  | 2021-02-11 | 2021-02-14 | 2021-02-11 | 2021-02-13 | 5 | 3
Team 3 | Andrew & Hossam | RTM & SIQ |  | 2021-02-11 | 2021-02-14 | 2021-02-11 | 2021-02-13 | 4 | 2
Second Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Team 1 | Nour & Hossam | 1-Modify HSI Document | Apply the modification on HSI as agreed in the modification document. | 2021-02-18 | 2021-02-20 | 2021-02-19 | 2021-02-20 | 2
Team 2 | Andrew & Habiba | 1- Modify CRS | Apply the modification on CRS as agreed in the modification document. | 2021-02-18 | 2021-02-20 | 2021-02-19 | 2021-02-20 | 2
Team 3 | Abdullah & Nihal | 1- RTM & SIQ | Apply the modification in RTM & SIQ as agreed in the modification document. | 2021-02-18 | 2021-02-20 | 2021-02-19 | 2021-02-20 | 2
Team 1 | Nour & Hossam | Review On RTM & SIQ | Deliver a review sheet containing all the issues found in the RTM & SIQ | 2021-02-20 | 2021-02-21 | 2021-02-21 | 2021-02-22 | 1
Team 2 | Andrew & Habiba | Review on HSI | Deliver a review sheet containing all the issues found in the HSI. | 2021-02-20 | 2021-02-21 | 2021-02-21 | 2021-02-22 | 1
Team 3 | Abdullah & Nihal | Review on CRS | Deliver a review sheet containing all the issues found in the CRS | 2021-02-20 | 2021-02-21 | 2021-02-21 | 2021-02-22 | 1
Third Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Task 0 | Abdullah | - Project Plan | - Add project plan for week 3 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2
Task 1 | Habiba | -Modify the CR & CRS | -Add the new Customer Requirements from SIQ to CR. -Reflect these changes on CRS | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0.5 | 0.5
Task 2 | Nour | - Modify HSI | Reflect the CR changes on HSI | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0.5 | 0.5
Task 3 | Abdullah | - Draw the SRS Context diagram | -Use the CRS context Diagram with requirements & HSI context Diagram to SRS Context diagram | 2021-03-04 | 2021-03-05 | 2021-03-04 | 2021-03-05 | 4 | 4
Task 4 | Andrew | - Draw the SRS Context diagram | -Use the CRS context Diagram with requirements & HSI context Diagram to SRS Context diagram | 2021-03-04 | 2021-03-05 | 2021-03-04 | 2021-03-05 | 4 | 4
Task 7 | Habiba | -SRS Requirements section | -Cover the CRS Reqs and divide them into moer specific Software requirements while taking the SRS context diagram into considration . | 2021-03-05 | 2021-03-06 | 2021-03-05 | 2021-03-07 | 4 | 6
Task 8 | Nihal | -SRS Requirements section | -Cover the CRS Reqs and divide them into more specific Software requirements while taking the SRS context diagram into considration . | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-07 | 4 | 6
Task 5 | Nour | - Recolour all the documnets | - Give all the documents the same colour with the same format | 2021-03-04 | 2021-03-05 | 2021-03-05 |  | 1
Task 6 | Hossam | -Update the RTM | - ADDThe SRS Reqs to the RTM | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-08 | 1 | 2
Task 7 | Nour | - Review the SRS context diagram | - Review on the SRS context diagram | 2021-03-05 | 2021-03-06 | 2021-03-06 | 2021-03-09 | 1 | 0.5
Task 8 | Hossam | -Review the SRS requirements | - ADDThe SRS Reqs to the RTM | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-08 | 3 | 2
Task 9 | Andrew | - Review the RTM | - Review on the new added reqs in the RTM | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 0.5 | 0.5