## Project Plan
Sovy - Digital Calculator PO1_DGC
First Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Team 1 | Nour & Nihal | HSI Document |  | 2021-02-11 | 2021-02-14 | 2021-02-11 | 2021-02-14 | 5 | 3
Team 2 | Habiba & Abdullah | CRS |  | 2021-02-11 | 2021-02-14 | 2021-02-11 | 2021-02-13 | 5 | 3
Team 3 | Andrew & Hossam | RTM & SIQ |  | 2021-02-11 | 2021-02-14 | 2021-02-11 | 2021-02-13 | 4 | 2
Second Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Team 1 | Nour & Hossam | 1-Modify HSI Document | Apply the modification on HSI as agreed in the modification document. | 2021-02-18 | 2021-02-20 | 2021-02-19 | 2021-02-20 | 2
Team 2 | Andrew & Habiba | 1- Modify CRS | Apply the modification on CRS as agreed in the modification document. | 2021-02-18 | 2021-02-20 | 2021-02-19 | 2021-02-20 | 2
Team 3 | Abdullah & Nihal | 1- RTM & SIQ | Apply the modification in RTM & SIQ as agreed in the modification document. | 2021-02-18 | 2021-02-20 | 2021-02-19 | 2021-02-20 | 2
Team 1 | Nour & Hossam | Review On RTM & SIQ | Deliver a review sheet containing all the issues found in the RTM & SIQ | 2021-02-20 | 2021-02-21 | 2021-02-21 | 2021-02-22 | 1
Team 2 | Andrew & Habiba | Review on HSI | Deliver a review sheet containing all the issues found in the HSI. | 2021-02-20 | 2021-02-21 | 2021-02-21 | 2021-02-22 | 1
Team 3 | Abdullah & Nihal | Review on CRS | Deliver a review sheet containing all the issues found in the CRS | 2021-02-20 | 2021-02-21 | 2021-02-21 | 2021-02-22 | 1
Third Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Task 0 | Abdullah | - Project Plan | - Add project plan for week 3 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2 | 2
Task 1 | Habiba | -Modify the CR & CRS | -Add the new Customer Requirements from SIQ to CR. -Reflect these changes on CRS | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0.5 | 0.5
Task 2 | Nour | - Modify HSI | Reflect the CR changes on HSI | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0.5 | 0.5
Task 3 | Abdullah | - Draw the SRS Context diagram | -Use the CRS context Diagram with requirements & HSI context Diagram to SRS Context diagram | 2021-03-04 | 2021-03-05 | 2021-03-04 | 2021-03-05 | 4 | 4
Task 4 | Andrew | - Draw the SRS Context diagram | -Use the CRS context Diagram with requirements & HSI context Diagram to SRS Context diagram | 2021-03-04 | 2021-03-05 | 2021-03-04 | 2021-03-05 | 4 | 4
Task 7 | Habiba | -SRS Requirements section | -Cover the CRS Reqs and divide them into moer specific Software requirements while taking the SRS context diagram into considration . | 2021-03-05 | 2021-03-06 | 2021-03-05 | 2021-03-07 | 4 | 6
Task 8 | Nihal | -SRS Requirements section | -Cover the CRS Reqs and divide them into more specific Software requirements while taking the SRS context diagram into considration . | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-07 | 4 | 6
Task 5 | Nour | - Recolour all the documnets | - Give all the documents the same colour with the same format | 2021-03-04 | 2021-03-05 | 2021-03-05 |  | 1
Task 6 | Hossam | -Update the RTM | - ADDThe SRS Reqs to the RTM | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-08 | 1 | 2
Task 7 | Nour | - Review the SRS context diagram | - Review on the SRS context diagram | 2021-03-05 | 2021-03-06 | 2021-03-06 | 2021-03-09 | 1 | 0.5
Task 8 | Hossam | -Review the SRS requirements | - ADDThe SRS Reqs to the RTM | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-08 | 3 | 2
Task 9 | Andrew | - Review the RTM | - Review on the new added reqs in the RTM | 2021-03-06 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 0.5 | 0.5
Forth Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Task 0 | Abdullah | - Project Plan | - Add project plan for week 4 | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-10 | 2 | 2
Task 1 | Habiba | -Modify the SRS requirments | -Modify your SRS requirments | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-10 | 3 | 2
Task 2 | Abdullah | - Modify the context diagram | - Modify the context diagram in the SRS according to the last review | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-10 | 1
Task 3 | Hossam | -Update the RTM | -make the RTM more readable, and add the last modifications as per the SRS,HSI and CRS | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-11 | 1
Task 4 | Nour | - Modify the CRS | - Modify the CRS as per the last review | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-11 | 1
Task 5 | Andrew | -Modify the CRS | -Add the lcd initilization sequence,and update the document as per the last review | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-11 | 1
Task 6 | Nour | - Recolour all the documnets | - Give all the documents the same colour with the same format | 2021-03-10 | 2021-03-11 | 2021-03-10 |  | 2
Task 7 | Nihal | - Review the RTM | - Review the RTM | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-11 | 1
Task 8 | Andrew | -Review the SRS requirements | -Review the SRS requirements | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-11 | 2
Task 9 | Hossam | -Review the SRS context diagram | -Review the SRS context diagram | 2021-03-10 | 2021-03-11 | 2021-03-10 | 2021-03-11 | 1
Fifth Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Task 0 | Abdullah | - Project Plan | - Add project plan for week 5 | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 2 | 2
Task 1 | Hossam | -Modify the SRS requirments | -Modify SRS requirments according to the last review then release it | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 1 | 1
Task 2 | Hossam | -Update the RTM | -make the RTM more readable, and add the last modifications as per the SRS,HSI and CRS | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 1 | 1
Task 3 | Abdullah | -MCAL Layer APIs | -Write down the MCAL layer APIs, according to the static Design | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 1 | 0.5
Task 4 | Nour | - App Layer APIs | -Write down the APP layer APIs, according to the static Design | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 1 | 1
Task 5 | Andrew | - App Layer APIs + Lib | -Continue Writing the APP layer APIs+ Lib Layer, according to the static Design | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 1 | 1
Task 6 | Nour | - Recolour all the documnets | - Give all the documents the same colour with the same format | 2021-04-05 | 2021-04-07 | 2021-04-05 |  | 2
Task 7 | Nihal | - Diagrams | - Draw the Context Diagram, input/output signal and static architecture diagrams | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 1 | 2
Task 8 | Habiba | - HAL Layer APIs | -Write down the HAL layer APIs, according to the static Design | 2021-04-05 | 2021-04-07 | 2021-04-05 | 2021-04-07 | 2 | 3
Sixth Week's Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Task 0 | Abdullah | - Project Plan | - Add project plan for week 6 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2 | 2
Task 1 | Hossam | -Update the GDD | -Apply the GDD changes to RTM - names of Req IDS - return type enum and add their values E_OK -> 0,E_NOK -> 1 -remove the switch , Display and play tone APIs | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 3 | 1
Task 2 | Nihal | -Update the GDD | -Update the Diagrams as agreed in the team meeting | 2021-04-14 | 2021-04-16 | 2021-04-14 | 2021-04-14 | 1 | 0.5
Task 3 | Habiba | -Review on the GDD | -Review on the Whole GDD after modifications | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 1 | 1
Task 4 | Nour | - LCD + Buzzer CDDs | -Write down the LCD and Buzzer comments that generates the CDD for these modules | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 2 | 2
Task 5 | Andrew | - keypad manager + Math_Calc CDDs | -Write down the keypad manager and Math_Calc comments that generates the CDD for these modules | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 3 | 3.5
Task 6 | Nour | - Recolour all the documnets | - Give all the documents the same colour with the same format | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 2 | 2.5
Task 7 | Abdullah | - Operation manager | -Write down the Operation manager comments that generates the CDD for these modules | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 3 | 2.5
Task 8 | Habiba | - Timer + Keypad CDDs | -Write down the Keypad and Timer comments that generates the CDD for these modules | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 3 | 2.5
Task 9 | Nihal | - Dio + Port | -Write down the Dio and Port comments that generates the CDD for these modules | 2021-04-14 | 2021-04-16 | 2021-04-14 |  | 2 | 2
Final Sprint Plan
| Team Members | Tasks | Task Description | Assignation Date | Deadline Date | Checking Date | Delivery Date | Estimation (hrs) | Real time (hrs)
Task 0 | Abdullah | - Final Plan | - Add project plan for the last Sprint | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 1 | 1
Task 1 | Abdullah | - Review CR & CYRS & HSI | - Make sure that all the customer requirement are coreectly covered in the CYRS and HSI, Add the found review points in the review sheet | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2 | 2
Task 2 | Nihal | -Review SRS | -Make sure that all the CYRS and HSI are covered in the SRS, Add the found review points in the review sheet | 2021-04-24 | 2021-04-24 | 2021-04-24 |  | 2
Task 3 | Habiba | -Review on the GDD | -Review on the Whole GDD after modifications,Add the found review points in the review sheet | 2021-04-25 | 2021-04-25 | 2021-04-24 | 2021-04-25 | 1 | 1
Task 4 | Hossam | -Review RTM | -Update the Diagrams as agreed in the team meeting ,Add the found review points in the review sheet | 2021-04-25 | 2021-04-25 | 2021-04-24 |  | 1 | 0.5
Task 5 | Nour & Andrew | - Search on the CDD tools | - Search on how to use Doxygen and graphiz tools and make a template for the rest of the team to use | 2021-04-24 | 2021-04-25 | 2021-04-24 | 2021-04-25 | 2 | 2021-02-01
CDD Phase
Task 1 | Abdullah | LCD + Integration | LCD + Integration Modules CDD using the Doxygen tool | 2021-04-29 | 2021-05-03 | 2021-04-29 |  | 4
Task 2 | Nihal | Timer + Buzzer | Timer + Buzzer Modules CDD using the Doxygen tool | 2021-04-29 | 2021-05-03 | 2021-04-29 |  | 4
Task 3 | Habiba | Keypad + Keypad manager | Keypad + Keypad manager Modules CDD using the Doxygen tool | 2021-04-29 | 2021-05-03 | 2021-04-29 |  | 4
Task 4 | Hossam | Operation Manager | Operation Manager Modules CDD using the Doxygen tool | 2021-04-29 | 2021-05-03 | 2021-04-29 |  | 4
Task 5 | Nour | dio + port | dio + port Modules CDD using the Doxygen tool | 2021-04-29 | 2021-05-03 | 2021-04-29 |  | 4
Task 6 | Andrew | Math_Calc | Math_Calc Modules CDD using the Doxygen tool | 2021-04-29 | 2021-05-03 | 2021-04-29 |  | 4
Code implementation Phase